## SPP Status Check - Master Sheet
Directions: Initial Setup (to be completed prior to Act 2, Event 6): Step 1: Enter your school-specific goals from your School Performance Plan - A Roadmap to Success under School Goal 1, 2, and 3. You can add or remove goals as needed. Select the NDE STIP Goal the school goal aligns with in the Connects To... drop-down menu. Step 2: For each goal, add the Improvement Strategies, Intended Outcomes, and dates for each event from the SPP Roadmap. Note: The Goals, Improvement Strategies, Intented Outcomes, and dates you enter on this tab will auto-populate the subsequent tabs. Similarly, information you enter on tabs 2-5 will automatically populate this tab.
School Goal |  | Select aligned STIP goal below: |  |  | Did we achieve our goal?
As a school, combined grade bands will score an average of 1% above the state proficiency average on state math assessments; Grades 3-8 combined SBAC proficiency & Grades K-2 combined MAP |  | Nevada Education Goal 3: All students experience continued academic growth
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Event 7: Status Check 2 (Insert Date) | Event 8: Status Check 3 (Insert Date) | Were our improvement strategies successful?
Language Objectives | Teachers will collaborate, scaffold, and differentiate instruction. |  | 2022-03-16 | 2022-06-01
High Level DOK Questions - Tier 1 and Intervention | Teacher collaboration, differentiate instruction |  | 2022-03-16 | 2022-06-01
Focus on Essential Standards for Instruction - Tier 1 and Intervention | Teacher Collaboration |  | 2022-03-16 | 2022-06-01
School Goal |  | Select aligned STIP goal below: |  |  | Did we achieve our goal?
Train teachers with social emotional curriculum and grade-level curriculum so they are better prepared to be effective teachers |  | Nevada Education Goal 6: All students and adults learn and work together in safe environments where identities and relationships are valued and celebrated
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Event 7: Status Check 2 (Insert Date) | Event 8: Status Check 3 (Insert Date) | Were our improvement strategies successful?
SEL Training | Teachers feel more safe, stable, and confident in their ability to effectively teach their class and manage their workload |  | 2022-03-16 | Strong
Curriculum: Mentoring and preparation | Teachers will feel confident in their ability to teach the curriculum, to prepare lesson plans, and mentor other teachers. |  | 2022-03-16
School Goal |  | Select aligned STIP goal below: |  |  | Did we achieve our goal?
The school will provide constant and direct communication about school events that involve students, staff, families and community by providing information through at least two different facets. |  | Nevada Education Goal 5: All students have access to new and continued educational opportunities supported by funding that is administered transparently consistently and in accordance with legislative or grant guidelines
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Event 7: Status Check 2 (Insert Date) | Event 8: Status Check 3 (Insert Date) | Were our improvement strategies successful?
Constant communication to families. | Building school community in a consistent manner |  | 2022-03-16 | Strong
School Goal |  | Select aligned STIP goal below: |  |  | Did we achieve our goal?
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Event 7: Status Check 2 (Insert Date) | Event 8: Status Check 3 (Insert Date) | Were our improvement strategies successful?
(insert improvement strategies here) | (insert intended outcomes here)
School Goal |  | Select aligned STIP goal below: |  |  | Did we achieve our goal?
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Event 7: Status Check 2 (Insert Date) | Event 8: Status Check 3 (Insert Date) | Were our improvement strategies successful?
(insert improvement strategies here) | (insert intended outcomes here)

## Event 6 Status Check 1
Directions: As a team, for each goal: Step 1: Review the Findings/Visualizations slides within the Events 6-8 slide deck. These will need to be updated prior to each event. Step 2: Reflect on the Now, Next, Need questions noted in the slide deck. Step 3: Fill in the appropriate cells for Event 6. - Rate the overall status of the improvement strategy using one of the following: Strong - on track; At Risk - requires some refinement and/or support; or Needs Immediate Attention - requires immediate support - Identify specific Lessons Learned (Now), Next Steps and Needs Note: The rating you enter for Step 3 will automatically update the accompanying cell on the Master Tracker (tab 1).
School Goal
As a school, combined grade bands will score an average of 1% above the state proficiency average on state math assessments; Grades 3-8 combined SBAC proficiency & Grades K-2 combined MAP
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Language Objectives | Teachers will collaborate, scaffold, and differentiate instruction.
High Level DOK Questions - Tier 1 and Intervention | Teacher collaboration, differentiate instruction
#REF! | Teacher Collaboration
School Goal
Train teachers with social emotional curriculum and grade-level curriculum so they are better prepared to be effective teachers
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
SEL Training | Teachers feel more safe, stable, and confident in their ability to effectively teach their class and manage their workload
Curriculum: Mentoring and preparation | Teachers will feel confident in their ability to teach the curriculum, to prepare lesson plans, and mentor other teachers.
School Goal
The school will provide constant and direct communication about school events that involve students, staff, families and community by providing information through at least two different facets.
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Constant communication to families. | Building school community in a consistent manner
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)

## Event 7 Status Check 2
Directions: As a team, for each goal: Step 1: Review the Findings/Visualizations slides within the Events 6-8 slide deck. These will need to be updated prior to each Event. Step 2: Reflect on the Now, Next, Need questions noted in the slide deck. Step 3: Fill in the appropriate cells for Event 7. - Rate the overall status of the improvement strategy using one of the following: Strong - on track; At Risk - requires some refinement and/or support; or Needs Immediate Attention - requires immediate support - Identify specific Lessons Learned (Now), Next Steps and Needs Note: The rating you enter for Step 3 will automatically update the accompanying cell on the Master Tracker (tab 1).
School Goal
As a school, combined grade bands will score an average of 1% above the state proficiency average on state math assessments; Grades 3-8 combined SBAC proficiency & Grades K-2 combined MAP
Improvement Strategies | Intended Outcomes | Event 7: Status Check 2 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Language Objectives | Teachers will collaborate, scaffold, and differentiate instruction. | Strong | Although implementation of learning objectives varies in effectiveness, all teachers ensure that language objectives and purpose for learning are established at the beginning of each lesson. | Professional development and instructional coaching for all teachers will contine for the remainder of the year. Administration will provide feedback to teachers after classroom observations. | Administrative team needs to be more consistent with classroom observations and inspect what we expect. Classroom teachers need to hold themselves accountable.
High Level DOK Questions - Tier 1 and Intervention | Teacher collaboration, differentiate instruction | Strong | Although implementation of high level questioning varies in effectiveness, all teachers ensure that high level questioning is established throughout the lesson. | Professional development and instructional coaching for all teachers will contine for the remainder of the year. Administration will provide feedback to teachers after classroom observations. | Administrative team needs to be more consistent with classroom observations and inspect what we expect. Classroom teachers need to hold themselves accountable.
Focus on Essential Standards for Instruction - Tier 1 and Intervention | Teacher Collaboration | Strong | The PLC process whereby teachers focus on essential standards occurs in all classrooms, however the effectiveness of implementation varies. | Continued administrative support in PLC meetings and on-going professional development. | Increased teacher buy-in of the PLC process.
School Goal
Train teachers with social emotional curriculum and grade-level curriculum so they are better prepared to be effective teachers
Improvement Strategies | Intended Outcomes | Event 7: Status Check 2 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
SEL Training | Teachers feel more safe, stable, and confident in their ability to effectively teach their class and manage their workload | Strong | SEL training has been well recieved and has been implimented for teachers and students. | Continue with ongoing professional development and SEL support. | Continued district support for further SEL training and resources.
Curriculum: Mentoring and preparation | Teachers will feel confident in their ability to teach the curriculum, to prepare lesson plans, and mentor other teachers. | Strong | The instructional coach consitently works with teachers regarding curriculum, lesson planning, and high yield instructional strategies. | The instructional coach will continue with the same levels of support. | Teachers who are resistent to instructional coaching need to be held accountable by administration.
School Goal
The school will provide constant and direct communication about school events that involve students, staff, families and community by providing information through at least two different facets.
Improvement Strategies | Intended Outcomes | Event 7: Status Check 2 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Constant communication to families. | Building school community in a consistent manner | Strong | Overall as a school, we communicate effectively via whole school, individual classrooms, and as needed for other events. | We will continue with how we currently communicate to our community. | We will check the end of the year parent surveys and make any necessary adjustments.
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 7: Status Check 2 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 7: Status Check 2 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)

## Event 8 Status Check 3
Directions: As a team, for each goal: Step 1: Review the Findings/Visualizations slides within the Events 6-8 slide deck. These will need to be updated prior to each event. Step 2: Reflect on the Now, Next, Need questions noted in the slide deck. Step 3: Fill in the appropriate cells for Event 8. - Rate the overall status of the improvement strategy using one of the following: Strong - on track; At Risk - requires some refinement and/or support; or Needs Immediate Attention - requires immediate support - Identify specific Lessons Learned (Now), Next Steps and Needs Note: The rating you enter for Step 3 will automatically update the accompanying cell on the Master Tracker (tab 1).
School Goal
As a school, combined grade bands will score an average of 1% above the state proficiency average on state math assessments; Grades 3-8 combined SBAC proficiency & Grades K-2 combined MAP
Improvement Strategies | Intended Outcomes | Event 8: Status Check 3 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Language Objectives | Teachers will collaborate, scaffold, and differentiate instruction. | Strong | Although implementation of learning objectives varies in effectiveness, all teachers ensured that language objectives and purpose for learning were established at the beginning of each lesson. | Professional development and instructional coaching continued until the end of the year. Administration almost always provided feedback to teachers after classroom observations. | Administrative team needs to be more consistent with classroom observations and inspect what we expect. Classroom teachers need to hold themselves accountable.
High Level DOK Questions - Tier 1 and Intervention | Teacher collaboration, differentiate instruction | Strong | Although implementation of high level questioning varies in effectiveness, all teachers ensured that high level questioning was established throughout the lesson. | Professional development and instructional coaching for all teachers will continued until the end of the year. Administration almost always provided feedback to teachers after classroom observations. | Administrative team needs to be more consistent with classroom observations and inspect what we expect. Classroom teachers need to hold themselves accountable.
Focus on Essential Standards for Instruction - Tier 1 and Intervention | Teacher Collaboration | Strong | The PLC process whereby teachers focused on essential standards occured in all classrooms, however the effectiveness of implementation varied. | Continued administrative support in PLC meetings and on-going professional development occurred up to the end of the school year. A summer retreat is planned in July to provide PD for PLC and RTI for upcoming lead teachers for the 22/23 school year. | Increased teacher buy-in of the PLC process.
School Goal
Train teachers with social emotional curriculum and grade-level curriculum so they are better prepared to be effective teachers
Improvement Strategies | Intended Outcomes | Event 8: Status Check 3 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
SEL Training | Teachers feel more safe, stable, and confident in their ability to effectively teach their class and manage their workload | Strong | SEL training has been well received and has been implemented for teachers and students. | Continued with ongoing professional development and SEL support. | Continued district support for further SEL training and resources.
Curriculum: Mentoring and preparation | Teachers will feel confident in their ability to teach the curriculum, to prepare lesson plans, and mentor other teachers. | Strong | The instructional coach consistently worked with teachers regarding curriculum, lesson planning, and high yield instructional strategies. | The instructional coach continued with the same levels of support until the end of the year. | Teachers who were resistant to instructional coaching were held accountable by administration.
School Goal
The school will provide constant and direct communication about school events that involve students, staff, families and community by providing information through at least two different facets.
Improvement Strategies | Intended Outcomes | Event 8: Status Check 3 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Constant communication to families. | Building school community in a consistent manner | Strong | Overall as a school, we communicate effectively via whole school, individual classrooms, and as needed for other events. | We continued to communicate with our community consistently until the end of the year and we will communicate over the summer as appropriate and necessary. | We will check the end of the year parent surveys and make any necessary adjustments.
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 8: Status Check 3 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 8: Status Check 3 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)

## Event 9 Reviewing Our Journey
Directions: As a team, for each Goal: Step 1: Review the Findings/Visualizations slides within the Event 9 slide deck. These will need to be updated prior to each event. Step 2: Reflect on the Now, Next, Need questions noted in the slide deck. Step 3: Fill in the appropriate cells in the table below. - Did we achieve our Goal/Intended Outcomes - Yes, No. - Do we continue, correct, or cancel our goals/implementation strategies - Continue, Correct, Cancel. - Identify specific Lessons Learned, Next Steps and Needs. Note: The rating you enter for Step 3 will automatically update the accompanying cell on the Master Tracker (tab 1).
School Goal |  | Did we achieve our goal?
As a school, combined grade bands will score an average of 1% above the state proficiency average on state math assessments; Grades 3-8 combined SBAC proficiency & Grades K-2 combined MAP
Improvement Strategies | Intended Outcomes | Were our improvement strategies successful? (Select One) | Continue, Correct, or Cancel the Strategy? (Select One) | Now (Lessons Learned) | Next (Next Steps) | Need
Language Objectives | Teachers will collaborate, scaffold, and differentiate instruction.
High Level DOK Questions - Tier 1 and Intervention | Teacher collaboration, differentiate instruction
#REF! | Teacher Collaboration
School Goal |  | Did we achieve our goal?
Train teachers with social emotional curriculum and grade-level curriculum so they are better prepared to be effective teachers
Improvement Strategies | Intended Outcomes | Were our improvement strategies successful? (Select One) | Continue, Correct, or Cancel the Strategy? (Select One) | Now (Lessons Learned) | Next (Next Steps) | Need
SEL Training | Teachers feel more safe, stable, and confident in their ability to effectively teach their class and manage their workload
Curriculum: Mentoring and preparation | Teachers will feel confident in their ability to teach the curriculum, to prepare lesson plans, and mentor other teachers.
School Goal |  | Did we achieve our goal?
The school will provide constant and direct communication about school events that involve students, staff, families and community by providing information through at least two different facets.
Improvement Strategies | Intended Outcomes | Were our improvement strategies successful? (Select One) | Continue, Correct, or Cancel the Strategy? (Select One) | Now (Lessons Learned) | Next (Next Steps) | Need
Constant communication to families. | Building school community in a consistent manner
School Goal |  | Did we achieve our goal?
(insert goal here)
Improvement Strategies | Intended Outcomes | Were our improvement strategies successful? (Select One) | Continue, Correct, or Cancel the Strategy? (Select One) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
School Goal |  | Did we achieve our goal?
(insert goal here)
Improvement Strategies | Intended Outcomes | Were our improvement strategies successful? (Select One) | Continue, Correct, or Cancel the Strategy? (Select One) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)

## For Lists (hidden)
Nevada Education Goal 1: All children birth through third grade have access to quality early care and education
Nevada Education Goal 2: All students have access to effective educators
Nevada Education Goal 3: All students experience continued academic growth
Nevada Education Goal 4: All students graduate future-ready and globally prepared for postsecondary success and civic life
Nevada Education Goal 5: All students have access to new and continued educational opportunities supported by funding that is administered transparently consistently and in accordance with legislative or grant guidelines
Nevada Education Goal 6: All students and adults learn and work together in safe environments where identities and relationships are valued and celebrated